## QCR
Assymex Monterrey S.A. de C.V.
QUALITY CONTROL REPORT (10D)
QCR |  | 18763 | [5 empty] | Date: |  |  |  |  | 2024-07-18
AssyMex Contact / Title: |  | Daniel Morales | [5 empty] | Supplier Contact / Title: |  |  |  |  | Martín Sosa / SQE
Contact Phone: |  | 8128607691 | [5 empty] | Contact Phone: |  |  |  |  | N/A
Email: |  | daniel.morales@avcarbon.com | [5 empty] | Contact Email: |  |  |  |  | martin_sosa@tricoplastic.com
ONLY FILL THIS SECTION FOR INTERNAL SITUATIONS DETECTED AT ASSYMEX PLANT
|  | INTERNAL PPM | [6 empty] | INTERNAL AUDIT BY IATF
|  | EXTERNAL AUDIT BY CUSTOMER | [6 empty] | INTERNAL METRIC:
|  | EXTERNAL AUDIT BY IATF | [6 empty] | OTHER:
ONLY FILL THIS SECTION FOR QUALITY PROBLEMS DETECTED WITH CUSTOMER
Level 1 - Customer Return - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 2 - Quality Rejection - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 3 - Quality Concern - Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
All Incoming stock 100% certified.
Level 4 - Notification - All Incoming stock 100% certified.
WHAT IS THE PROBLEM ? > Use 4W + 2H to know what is the Current Situation ? Customer View and AssyMex View
- What happened? Description of the Problem |  | Innoperative motor caused for short circuit between housing and low speed | [7 empty] | - Why is it a problem? |  | Low performance of motor with final customer
BAD PART | [9 empty] | GOOD PART
- When it happened? Date: dd-mm-yyyy |  | 2024-07-17 | [6 empty] | - Where detected? Incoming, Production Line, Customer, Warranty, etc. |  |  | Customer production line
- How detected? |  | Energizing the motor | [6 empty] | - How many bad parts? |  |  | 4
Additional Information for Customer
Customer Part Number: |  | 95015-113 | [7 empty] | AssyMex Part Number: |  |  | 33-0161
Customer Lot Number: |  | 2024-06-28 | [7 empty] | AssyMex Lot Number: |  |  | 180 (28/07/24)
Additional Information:
Customer Inventory: |  | 3000 | [7 empty] | AssyMex Inventory: |  |  | 1344
In Transit Inventory: |  | 0 | [5 empty] | Logistic Platform Inventory:
Material Disposition
|  | Return to Supplier. | [5 empty] | Sort by Supplier. | [5 empty] | Sort / Rework by External Company
|  | RMA # | [11 empty] | WO #
|  | Scrap. Supplier's expense. | [5 empty] | Use as received | [5 empty] | Sort / Rework by AssyMex
WO #
CORRECTIVE ACTION REPORT - 10D REPORT
1.- | Problem Solving Team Members
| Leader: | Daniel Morales | [5 empty] | Title: | Quality Engineer |  |  |  |  | Phone:
| Email: | daniel.morales@avocarbon.com | [5 empty] | Fax: | N/A |  |  |  |  | Mobile:
| Group: | Orlando Salaza, Ramses Rendon
2.- | Describe the Problem
Innoperative motor caused for short circuit between housing and low speed
| - Was part reworked by supplier ? |  |  | NO | [5 empty] | - When was it manufactured ? |  |  |  | 2024-06-01
| - Are we capturing the defect when reinjecting product in normal process ? If YES, explain how ? |  |  | Yes, in electrical tester | [5 empty] | - Did a similar problem happen previously at AssyMex or internally ? If YES, when ? |  |  |  | Yes, 2022
3.- | Immediate Countermeasures / Problem Containment ? (24 hours)
IMMEDIATE COUNTERMEASURES IN SUPPLIER PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
Verify visually than soldering in tower has not solder burrs over the plastic tower | [8 empty] | Sortech |  |  | 2024-07-18 |  |  | Sortetch
IMMEDIATE COUNTERMEASURES IN AssyMex PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
Verify visually than soldering in tower has not solder burrs over the plastic tower | [8 empty] | Sughey Rangel |  |  | 2024-07-18 |  |  | AssyMex plant
Sorting Activity >> by Supplier
|  |  | Total Sorted |  | Total Bad Parts |  | PPM |  |  | Sorting Date | Responsible |  | Identification of OK Parts
- Suspect Inventory in Customer plant : |  |  | 3000 |  | 3 | = | 1000
- Suspect Inventory in AssyMex plant : |  |  | 1344 |  | 0 | = | '----'
- Suspect Inventory in Transit : |  |  | NA |  |  | = | '----'
- Suspect Inventory in Logistic platform : |  |  | NA |  |  | = | '----'
- Suspect Inventory in Supplier plant : |  |  | 0 |  | 0 | = | '----'
- Production dates of sorted parts: |  |  | From: |  |  | To: | [5 empty] | First Certified Good Shipment |  |  | Lot Number:
|  |  | 2024-07-10 |  |  | 2024-07-17 | [8 empty] | 170724
- Production dates of bad parts: |  |  | Oldest part: |  |  | Most recent part: | [8 empty] | Date:
|  |  | 2024-06-28 |  |  | 2024-06-28 | [8 empty] | 1707/24
4,1.- | Analysis and Root Cause - Ocurrence
5 x Why Analysis Form - Ocurrences Why did it happen?
LOW TEMPERATURE OF SOLDERING IRON
1st Why? |  | Question: Why was the soldering iron operating at low soldering temperature?
Answer: Because the resistor was not heating the soldering iron tip correctly.
2nd Why? |  | Question: Why was the resistor not heating the soldering iron tip correctly?
Answer: Because the tip does not make correct contact with the heating element to heat up
3rd Why? |  | Question : Why the tip does not make proper contact with the heating element to heat up?
Answer: Because there is a GAP between the soldering iron tip and the resistor.
4th Why? |  | Question: Why is there a GAP between the soldering iron tip and the resistor?
Answer: Because the thread connecting the soldering iron tip to the resistor has worn down during use.
5th Why? |  | Question: Why did the thread that connects the soldering iron tip to the resistor became worn down during use?
Answer: Because it was worn down
Specific root cause |  | Question:Why it was worn down?
Answer: The soldering iron worked more than its shelf time because it was not set in the daily Set-Up.
4,2 .- | Analysis and Root Cause - Non Detection
5 x Why Analysis Form - Non-Detection Why did the non-conformity escape?
Condition is not verified during the final inspection
1st Why? |  | Question: Why the condition was not verified at the final inspection? |  |  | 1st Why?
Answer: The operator is unknown about the condition to be inspected.
2nd Why? |  | Question: Because in the work instruction the defect was not mentioned. |  |  | 2nd Why?
Answer: Why was the defect not mentioned in their work instruction?
3rd Why? |  | Question: Because this type of failure is not considered in the PFMEA. |  |  | 3rd Why?
4th Why? |  |  |  |  | 4th Why? |  | Question:
Answer:
5th Why? |  |  |  |  | 5th Why? |  | Question:
|  | Answer: |  |  |  |  | Answer:
5.- | Corrective Action
To Eliminate Occurrence of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Change damage soldering iron |  |  |  |  | Eliminate conditon of burr | [6 empty] | Orlando Salazar | 2024-07-18 | 2024-07-18
| Update set up register sheet (Add verification of soldering iron) |  |  |  |  | Defect does not return | [6 empty] | Sughey Rangel | 2024-08-02 | 2024-08-02
| Update work instruction (Verification of soldering iron during the operation) |  |  |  |  | Defect does not return | [6 empty] | Sughey Rangel | 2024-08-02 | 2024-08-02
To Improve Detection of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Update inspection instruction to verify the soldering burrs is not over the plastic tower |  |  |  |  | Avoid scapes to customer | [6 empty] | Sughey Rangel | 2024-08-02 | 2024-08-02
| Create gage to verify that soldering in tower has not burr |  |  |  |  | Avoid scapes to customer | [6 empty] | Alicio flores | 2024-08-09
6,1.- | Implement and Verify Corrective Action - Occurences
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influent Factors | [9 empty] | Y
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
Y
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
Y
3- IS ALL DOCUMENTATION COHERENT?
Y
4- ARE THE INSTRUCTIONS CLEAR?
Y
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation | [9 empty] | Y
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
Y
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
Y
8- ARE OPERATORS AWARE OF THE DEFECT?
Y
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
Y
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid | [9 empty] | Y
11- IS THERE A VISUAL AID?
Y
12- IS IT POSTED ON A VISIBLE SPOT?
Y
13- IS THE CONTENT CLEAR?
Equipment | [9 empty] | Y
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
Y
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
Y
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
6,1.- | Implement and Verify Corrective Action - Non - Detection
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influential Factors | [9 empty] | Y
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
Y
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
Y
3- IS ALL DOCUMENTATION COHERENT?
Y
4- ARE THE INSTRUCTIONS CLEAR?
Y
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation | [9 empty] | Y
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
Y
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
Y
8- ARE OPERATORS AWARE OF THE DEFECT?
Y
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
Y
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid | [9 empty] | Y
11- IS THERE A VISUAL AID?
Y
12- IS IT POSTED ON A VISIBLE SPOT?
Y
13- IS THE CONTENT CLEAR?
Equipment | [9 empty] | Y
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
Y
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
Y
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
Quality Control Documentation | [9 empty] | Y
17- WAS THE PLAN CONTROL WITH THE CORRECTIVE ACTIONS UPDATED?
Y
18.- WAS THE PROCESS FMEA UPDATED WITH THE CORRECTIVE ACTIONS?
Y
19.- WAS THE WORK INSTRUCTION UPDATED WITH THE CORRECTIVE ACTIONS?
Y
20.- WAS THE QUALITY REGISTER UPDATED WITH THE CORRECTIVE ACTIONS?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
7.- | Preventive Action
| Preventive Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Update PFMEA to add failure type |  |  |  |  | Defect does not return | [6 empty] | Sughey Rangel | 2024-08-09 | 2024-08-09
| Update preventive maintenance |  |  |  |  | Defect does not return | [6 empty] | Ramses Rendon | 2024-08-09 | 2024-08-09
8.- | Standardize / Potential Applicability
| 1.- Potential Applicability of Corrective / Preventive Action to similar lines / products. | [12 empty] | Comments
| To whom? | Production Line: |  | Melco |  |  |  |  | When? |  | 2024-08-19
|  | Operation: |  | OP 170 |  |  |  |  | When? |  | 2024-08-19
|  | Product: |  | 33-0130 |  |  |  |  | When? |  | 2024-08-19
9.1.- | Evidence your Efforts - Ocurrences
Before Corrective Action | [9 empty] | After Corrective Action
9.2.- | Evidence your Efforts - Non Detection
Before Corrective Action | [9 empty] | After Corrective Action
10.- | Congratulate the Team
Certification label per box
Man power
Method
Enviromental
Machine
Material
Measurements
Solder burr over the plastic tower
Man power
Method
Enviromental
Machine
Material
Measurements
Part was not detected during the assymex process
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
Solder burr in tower over plastic tower
Soldering in tower without burrs
Low skills to solder for operator
Operators without training
Variation in the method of applying soldering for operators (Double cycle)
Lack of lighting
Worn soldering iron tip
Low temperature of soldering iron
Incorrect soldering iron tip
Incorrect soldering tin
Contaminated soldering tin
Contaminated tower (leadframe)
Condition is not verified during the final inspection
Low skills to inspect material for final inspector
Insuficcient lighting in final inspection
The fixture doesn't work correclty
Tester not judge a part with burr over the plastic
Note on B156: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B211: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B265: Corrective action Explain clearly which corrective actions are implemented to correct the root-cause. Reader should understand what is the difference between previous and future situation. Put data when appropriate, process parameter before and after for example. Define Due Dates for each Corrective Action.
Note on B282: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K284: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H318: Date of the audit: For every shift, record the date of audit
Note on H320: Decision: Tick Y or N to validate or not the result of the audit for each shift.
Note on B326: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K328: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H370: Date of the audit: For every shift, record the date of audit
Note on H372: Decision: Tick Y or N to validate or not the result of the audit for each shift.

## Add - Visual Aid
WHEN I FIND A BAD PART, WHAT SHOULD I DO?
Adhere to Quality Alert visual
Follow Reaction Plan
Process with Internal NNC
PROHIBITED OPERATIONS:
non-inspection
PERMITTED TOOLS:
Quality Alert
LEVEL | A | B | C | D | E | F | G
DATE LEVEL
WHO CREATE
Visual Aid
Describe the defect
Bad part
Good part

## LLC Occ
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## LLC NON-DET
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## Evidence Control Plan and PFMEA
CONTROL PLAN
PFMEA
INSERT HERE SCREENSHOT
OF CONTROL PLAN UPDATED
INSERT HERE SCREENSHOT
OF PFMEA UPDATED