## QCR
Assymex Monterrey S.A. de C.V.
QUALITY CONTROL REPORT (10D)
QCR |  | 18766 | [5 empty] | Date: |  |  |  |  | 2024-07-25
AssyMex Contact / Title: |  | Daniel Morales | [5 empty] | Customer Contact / Title: |  |  |  |  | Martin Sosa / SQE
Contact Phone: |  | 8128607691 | [5 empty] | Contact Phone: |  |  |  |  | N/A
Email: |  | daniel.morales@avocarbon.com | [5 empty] | Contact Email: |  |  |  |  | Martin.sosa@avocarbon.com
ONLY FILL THIS SECTION FOR INTERNAL SITUATIONS DETECTED AT ASSYMEX PLANT
|  | INTERNAL PPM | [6 empty] | INTERNAL AUDIT BY IATF
|  | EXTERNAL AUDIT BY CUSTOMER | [6 empty] | INTERNAL METRIC:
|  | EXTERNAL AUDIT BY IATF | [6 empty] | OTHER:
ONLY FILL THIS SECTION FOR QUALITY PROBLEMS DETECTED WITH CUSTOMER
Level 1 - Customer Return - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 2 - Quality Rejection - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 3 - Quality Concern - Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
All Incoming stock 100% certified.
Level 4 - Notification - All Incoming stock 100% certified.
WHAT IS THE PROBLEM ? > Use 4W + 2H to know what is the Current Situation ? Customer View and AssyMex View
- What happened? Description of the Problem |  | Was found in the production line a PCB without capacitor | [7 empty] | - Why is it a problem? |  | Cause poor performance in the motor
BAD PART | [9 empty] | GOOD PART
- When it happened? Date: dd-mm-yyyy |  | 2024-07-25 | [6 empty] | - Where detected? Incoming, Production Line, Customer, Warranty, etc. |  |  | Production line / Brushcard assembly
- How detected? |  | Visually (Operator) | [6 empty] | - How many bad parts? |  |  | 1
Additional Information for Customer
Customer Part Number: |  | 95015-127 | [7 empty] | AssyMex Part Number: |  |  | 33-0169
Customer Lot Number: |  | 2024-05-21 | [7 empty] | AssyMex Lot Number: |  |  | 142
Additional Information:
Customer Inventory: |  | 960 | [7 empty] | AssyMex Inventory:
In Transit Inventory: | [7 empty] | Logistic Platform Inventory:
Material Disposition
|  | Return to Supplier. | [5 empty] | Sort by Supplier. | [5 empty] | Sort / Rework by External Company
|  | RMA # | [11 empty] | WO #
|  | Scrap. Supplier's expense. | [5 empty] | Use as received | [5 empty] | Sort / Rework by AssyMex
WO #
CORRECTIVE ACTION REPORT - 10D REPORT
1.- | Problem Solving Team Members
| Leader: | Daniel Morales | [5 empty] | Title: | Quality Engineer |  |  |  |  | Phone: | N/A
| Email: | daniel.morales@avocarbon.com | [5 empty] | Fax: | N/A |  |  |  |  | Mobile: | 8128607691
| Group: | Sughey Rangel, Orlando Salazar, Ramses Rendon, Eduardo Rodriguez, Gabriel Cavazos
2.- | Describe the Problem
Missing capacitor
| - Was part reworked by supplier ? |  |  | N/A | [5 empty] | - When was it manufactured ? |  |  |  | 2024-05-21
| - Are we capturing the defect when reinjecting product in normal process ? If YES, explain how ? | [8 empty] | - Did a similar problem happen previously at AssyMex or internally ? If YES, when ? |  |  |  | NO
3.- | Immediate Countermeasures / Problem Containment ? (24 hours)
IMMEDIATE COUNTERMEASURES IN CUSTOMER PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
Inspect 100% material in customer warehouse | [8 empty] | Daniel Morales |  |  | 2024-07-26 |  |  | TRICO
IMMEDIATE COUNTERMEASURES IN AssyMex PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
Inspect 100% material in warehouse | [9 empty] | Sughey Rangel |  |  | 2024-07-26 |  | ASSYMEX
Sorting Activity >> by Supplier
|  |  | Total Sorted |  | Total Bad Parts |  | PPM |  |  | Sorting Date | Responsible |  | Identification of OK Parts
- Suspect Inventory in Customer plant : |  |  | 960 |  | 0 | = | '----'
- Suspect Inventory in AssyMex plant : |  |  | 0 |  | 0 | = | '----'
- Suspect Inventory in Transit : |  |  | NA |  |  | = | '----'
- Suspect Inventory in Logistic platform : |  |  | NA |  |  | = | '----'
- Suspect Inventory in Supplier plant : |  |  | TBD |  |  | = | '----'
- Production dates of sorted parts: |  |  | From: |  |  | To: | [5 empty] | First Certified Good Shipment |  |  | Lot Number:
No shipment
- Production dates of bad parts: |  |  | Oldest part: |  |  | Most recent part: | [8 empty] | Date:
4,1.- | Analysis and Root Cause - Ocurrence
5 x Why Analysis Form - Ocurrences Why did it happen?
1st Why? | Question:
Answer:
2nd Why? | Question:
Answer:
3rd Why? | Question:
Answer:
4th Why? | Question:
Answer:
5th Why? | Question:
Answer:
4,2 .- | Analysis and Root Cause - Non Detection
5 x Why Analysis Form - Non-Detection Why did the non-conformity escape?
1st Why? | Question:
Answer:
2nd Why? | Question:
Answer:
3rd Why? | Question:
Answer:
4th Why? | Question:
Answer:
5th Why? | Question:
Answer:
5.- | Corrective Action
To Eliminate Occurrence of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
To Improve Detection of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
6,1.- | Implement and Verify Corrective Action - Occurences
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influent Factors
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
3- IS ALL DOCUMENTATION COHERENT?
4- ARE THE INSTRUCTIONS CLEAR?
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
8- ARE OPERATORS AWARE OF THE DEFECT?
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid
11- IS THERE A VISUAL AID?
12- IS IT POSTED ON A VISIBLE SPOT?
13- IS THE CONTENT CLEAR?
Equipment
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
6,1.- | Implement and Verify Corrective Action - Non - Detection
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influential Factors
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
3- IS ALL DOCUMENTATION COHERENT?
4- ARE THE INSTRUCTIONS CLEAR?
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
8- ARE OPERATORS AWARE OF THE DEFECT?
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid
11- IS THERE A VISUAL AID?
12- IS IT POSTED ON A VISIBLE SPOT?
13- IS THE CONTENT CLEAR?
Equipment
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
Quality Control Documentation
17- WAS THE PLAN CONTROL WITH THE CORRECTIVE ACTIONS UPDATED?
18.- WAS THE PROCESS FMEA UPDATED WITH THE CORRECTIVE ACTIONS?
19.- WAS THE WORK INSTRUCTION UPDATED WITH THE CORRECTIVE ACTIONS?
20.- WAS THE QUALITY REGISTER UPDATED WITH THE CORRECTIVE ACTIONS?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
7.- | Preventive Action
| Preventive Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
8.- | Standardize / Potential Applicability
| 1.- Potential Applicability of Corrective / Preventive Action to similar lines / products. | [12 empty] | Comments
| To whom? | Production Line: | [6 empty] | When?
|  | Operation: | [6 empty] | When?
|  | Product: | [6 empty] | When?
9.1.- | Evidence your Efforts - Ocurrences
Before Corrective Action | [9 empty] | After Corrective Action
9.2.- | Evidence your Efforts - Non Detection
Before Corrective Action | [9 empty] | After Corrective Action
10.- | Congratulate the Team
Man power
Method
Enviromental
Machine
Material
Measurements
Man power
Method
Enviromental
Machine
Material
Measurements
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
Missing capacitor
Good Part picture, drawing or description
Good Part picture, drawing or description must be from the same size and same angle.
Show Good Part condition.
Note on B156: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B233: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B312: Corrective action Explain clearly which corrective actions are implemented to correct the root-cause. Reader should understand what is the difference between previous and future situation. Put data when appropriate, process parameter before and after for example. Define Due Dates for each Corrective Action.
Note on B338: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K340: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H374: Date of the audit: For every shift, record the date of audit
Note on H376: Decision: Tick Y or N to validate or not the result of the audit for each shift.
Note on B382: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K384: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H426: Date of the audit: For every shift, record the date of audit
Note on H428: Decision: Tick Y or N to validate or not the result of the audit for each shift.

## Add - Visual Aid
WHEN I FIND A BAD PART, WHAT SHOULD I DO?
Adhere to Quality Alert visual
Follow Reaction Plan
Process with Internal NNC
PROHIBITED OPERATIONS:
non-inspection
PERMITTED TOOLS:
Quality Alert
LEVEL | A | B | C | D | E | F | G
DATE LEVEL
WHO CREATE
Visual Aid
Describe the defect
Bad part
Good part

## LLC Occ
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## LLC NON-DET
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## Evidence Control Plan and PFMEA
CONTROL PLAN
PFMEA
INSERT HERE SCREENSHOT
OF CONTROL PLAN UPDATED
INSERT HERE SCREENSHOT
OF PFMEA UPDATED