## Sheet1
PROBLEM SOLVING - 8D METHOD ¦ 8D-20260527-013311 ¦ Spark emitted during welding and loosened shunt wire
D1 | Establishing a team
| Names and functions of the team members involved (Whether they have the authority and knowledge to contribute to solving the problem) | [8 empty] | Their roles in the process (e.g. Production, Quality, Maintenance, Engineering)
| Hongyan LI — supervisor / engineering | [7 empty] | TRUE | Production (operator, line leader, or supervisor)
[9 empty] | FALSE | Maintenance (if equipment is involved)
| Alec YAO — project_manager / engineering | [7 empty] | TRUE | Process or Manufacturing Engineering
[9 empty] | FALSE | Logistics / Supplier Quality (if relevant)
| Weijiang PENG — project_manager / quality | [7 empty] | TRUE | Team leader or project manager (if apply)
[9 empty] | FALSE | Quality
[9 empty] | FALSE | Other (if apply)
D2 | Problem Description
| BRUSH (BRUSH) produced at TIANJIN for US MOTOR WORKS presents spark emitted during welding and a loosened shunt wire on the carbon brush CPUN54D0122. This defect impacts the welding between the gasket and the wire body, affecting the welding operation for the ELECTRIC TRACTION MOTOR application. Issue linked to WELDING; classified as low (quality type: Quality Alert). First occurrence (repetition: 0). WHAT: The carbon brush CPUN54D0122 has spark emitted during welding and a loosened shunt wire. WHERE: Detected at US MOTOR WORKS JE plant (JE BU). WHEN: 2026-05-27 WHO: PQC / A23 WHY: The defect impacts the welding between the gasket and the wire body. HOW: Visual inspection. HOW MANY: 2 pcs Standard: WI AVOT-WI-JO-034-A2 Expected: Glue is not allowed to drip onto the surface of the copper wire; welding should occur without sparks and the shunt wire shall remain securely welded per CPUN54D0122 requirements. Observed: Glue observed on copper wire surface; spark emitted during welding and loosened shunt wire on carbon brush CPUN54D0122 (Appearance defect), detected by visual inspection; 2/2 pcs affected. |  |  |  |  | III. Photo of defected part or schema of deviated measurement
| II.Factor | Is a Problem |  | Is Not a problem
|  | Other part numbers/ customers/sites affected/lot affected |  | Part numberscustomers//sites not affected/lot numbers not affected
| Product | Carbon brush CPUN54D0122 shows spark emitted during welding and loosened shunt wire |  | Carbon brush 205041 does not show spark during welding and does not have loosened shunt wire
| Time | 2026-05-27 |  | Before 2026-05-27
| Lot | 20251113-01526 |  | 20260204-00161
| Pattern | 2 NOK pieces out of 160,000 inspected/produced with spark during welding and loosened shunt wire |  | 159,998 OK pieces out of 160,000 with no spark during welding and shunt wire not loosened
D3 | Containment Actions |  |  |  |  | 📎 acaa8a2c0c9f0b6fdce02e2bc717033f.jpg
| I. Defected part status | FALSE | Is it returned to AVOCarbon? | FALSE | Is it Isolated? Where? | 📎 eb7846a8491776aef694756ec6675486.jpg | TRUE | Identified: Customer detection by visual inspection (PQC / A23); linked to batch containment
📎 f16e712c5f9dd16b859370f8afddcc33.png
📎 AVOT-G-024-A0 供应商GP12操作指导书.pdf
| Location | Inventory |  | Actions |  | 📎 cpun54d0122_b.pdf |  |  |  | Results
| Supplier site |  |  |  |  | 📎 1023246 WI(1).pdf
In Transit
In Production floor
In Warehouse
| In customer site | 16000 pcs (batch 20251113-01526) |  | Batch isolated at JE site; all parts from this batch to be returned to Tianjin plant for disposition/investigation |  | JE site / customer containment (not specified) |  |  |  | Batch blocked from use; return to Tianjin initiated
Others
| III. Alert Comunicated to | TRUE | Production Shift Leaders | FALSE | Warehouse |  | FALSE | Customer Contact
| Alert # (QRQC log or NCR #): AVOT-2026-PD-003 | TRUE | Quality Control | FALSE | Maintenance |  | FALSE | Production Planner
| IV. Restart Production |  | 2026-06-02 |  |  | 20260204-00161 |  |  |  | Breakpoint label applied to certified parts
Weijiang PENG — Quality Manager (Tianjin)
Visual criteria verification prior to release
| V. Containment Responsible: | Bingren YUAN — Quality Supervisor (Tianjin)
D4 | Root Cause Analysis
I. Define potential root cause for 4M+ Environment -OCCURRENCE
| Material |  | Method |  | Machine
| Copper wire surface contamination by glue overflow (glue present on wire surface). |  | Manual needle dispensing and tray curing allows uncontrolled glue flow/overflow onto copper wire surface. |  | Grinding equipment not equipped with an automatic dispensing device.
| Glue on copper wire surface increases contact resistance/contaminates weld interface, contributing to sparking and weak joint. |  | No defined/validated dispensing standard (direction/volume/placement) to prevent glue entering weld area. |  | No dispensing poka-yoke/fixture to block glue from the weld zone.
| NOK samples show obvious glue marks; OK samples show none. |  | Failure mode 'glue overflow to copper wire' not identified in PFMEA; control plan did not require prevention/detection controls. |  | Equipment specification did not include automatic dispensing due to missing PFMEA/CP requirement. |  |  |  | Manual needle dispensing causes glue overflow onto the copper wire surface (weld area contamination), leading to sparking during welding and loosened shunt wire.
| Manpower |  | Environment
| Operator manual dispensing technique cannot control glue flow direction consistently. |  | Curing/wait on tray after dispensing can allow glue to flow before cure (no controlled containment). |  | T1
| Manual process dependent on operator skill; variation not prevented. |  | Open handling during wait-for-cure may allow glue migration before curing. |  | T2
| No risk-based requirement for operator qualification/verification for glue placement. |  | N/A |  | T3
II. 5 Whys (Ocurrence) for selected Root causes
| 1st Why? | Question: | Why did the defect (sparking during welding and loosened shunt wire) occur?
|  | Answer: | Glue overflowed onto the surface of the copper wire, contaminating the welding area and contributing to unstable welding (sparking) and weak attachment (loosened shunt).
| 2st Why? | Question: | Why did glue overflow onto the copper wire surface?
|  | Answer: | Because dispensing is manual, the glue flow direction cannot be controlled, leading to overflow.
| 3st Why? | Question: | Why is dispensing manual with no control of glue flow direction?
|  | Answer: | Because the equipment is not equipped with an automatic dispensing device.
| 4st Why? | Question: | Why is the equipment not equipped with an automatic dispensing device?
|  | Answer: | Because PFMEA / Control Plan requirements for this step were not determined.
| 5st Why? | Question: | Why were PFMEA / Control Plan requirements not determined for this failure mode?
|  | Answer: | Because this quality issue had never occurred before, the failure mode was not identified in the FMEA.
| The gluing process relies on manual needle dispensing (no automatic dispensing/poka-yoke) because the failure mode 'glue overflow onto copper wire contaminating weld area' was not identified in PFMEA and therefore not translated into Control Plan requirements, allowing glue overflow that causes welding sparking and shunt loosening. |  |  | Visual evidence: NOK sample copper wire shows obvious glue marks; qualified product copper wire shows no glue marks.
IV. Define potential root cause for 4M+ Environment-NON DETECTION
| Material |  | Method |  | Machine
| Copper wire appearance contamination by glue was not defined as a defect to be checked in the control plan/inspection WI. |  | No inspection method/acceptance criteria specified for glue contamination on copper wire; therefore no check was performed. |  | N/A (detection gap is in inspection standard, not equipment).
| Defective sealed samples for glue-contaminated copper wire were not available in the appearance selection reference set. |  | Appearance selection process lacked a reference standard for this defect type, leading to inconsistent/absent detection. |  | N/A.
| N/A |  | N/A |  | N/A |  |  |  | Control plan / inspection WI did not define glue-contamination check criteria for copper wire, so inspectors performed no check and contaminated wires were not detected before welding.
| Manpower |  | Environment
| Inspectors were not instructed/trained to check glue contamination due to missing requirements in WI. |  | N/A / not identified as a contributor for non-detection. |  | T1
| Selection relied on subjective judgement without defect sample reference. |  | N/A. |  | T2
| N/A |  | N/A |  | T3
V. 5 Whys (Non Detection) for selected Root causes
| 1st Why? | Question: | Why did the defect pass the inspection system?
|  | Answer: | Because no inspection was carried out to check glue contamination on the copper wire.
| 2st Why? | Question: | Why was no inspection carried out for glue contamination?
|  | Answer: | Because the control plan and operation instruction manual did not formulate management requirements/criteria for this check.
| 3st Why? | Question: | Why were management requirements/criteria not formulated?
|  | Answer: | The appearance selection inspection WI did not include this defect mode (glue contamination) as a controlled item with reference samples.
| 4st Why? | Question: | Why was the defect mode not included in the WI/reference samples?
|  | Answer: | Defective sealed samples for this defect were not established/maintained for the selection process.
| 5st Why? | Question: | Why were defective sealed samples not established/maintained?
|  | Answer: | The inspection standardization process did not require updating the defect sample set when new defect modes were observed.
| Non-detection occurred because the control plan/inspection WI had no defined requirement or acceptance criteria to check copper wire glue contamination, so inspectors performed no check and contaminated wires passed to welding. |  |  | Update the appearance selection inspection operation instruction to add sealed defective samples for this defect and verify inspectors can identify/sort the defect during the selection process.
D5 | CORRECTIVE ACTION | [6 empty] | D6. I. Implementation & Effectiveness Check
| I.Corrective Action for Occurrence |  |  |  | Responsible | Due Date |  | Imp Date |  | Evidence
| Install an automatic gluing device for the processing equipment to eliminate manual needle dispensing and prevent glue overflow contaminating the copper wire/weld area. |  |  |  | Luke Zhao - Facility/Maintenance Manager | 2026-06-01 |  | 2026-05-29 |  | 4dac269c6054007bf10d3a08abdcab07.png
| Update the Control Plan to include the glue overflow/contamination failure mode at the weld area with defined control method and reaction plan. |  |  |  | Alec Yao - Engineering Manager | 2026-06-05 |  | 2026-05-29 |  | AVOT-WI-JE-010-A2
| II.Corrective Action for Detection |  |  |  | Responsible | Due Date |  | Imp Date |  | Evidence
| Update the appearance selection inspection WI to add visual inspection judgment criteria for copper wire glue contamination ("The surface of the copper wire is not allowed to be contaminated with glue"; any contamination = NG) and include sealed/cover defect samples as reference for inspectors during selection. |  |  |  | Hongyan Li (Engineering Supervisor, Tianjin) | 2026-05-29 |  | 2026-05-29 |  | AVOT-Q-20260529
D6 | II. Implementation & Effectiveness Check |  |  |  | III. Implementation & Effectiveness Check |  |  |  |  | Shift 1 | Shift 1 | Shift 1
| Monitoring intervale of time | 1 shift |  |  | Have parameters been corrected in safety/ working instructions? |  |  |  |  | TRUE | FALSE | FALSE
| Number of pieces produced | 3000 |  |  | Do working instructions match with Control Plan and PFMEA? |  |  |  |  | TRUE | FALSE | FALSE
| Rejection rate | 0 |  |  | Are the instruction clear? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Are crtitical points clearly described? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Does actual process match with the operating instructions |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Does actual process match with the expected corrective actions? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Are operators aware of the incident? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Are operators training about all process modification? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Has the solution properly validated in the floorshop? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Is there a clear visual aid published in visible spot? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Is the equipment modified vs the corrective actions? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Is the maintenance record modified? |  |  |  |  | TRUE | FALSE | FALSE
[5 empty] | Is the set up instruction modified? Match with CP? |  |  |  |  | TRUE | FALSE | FALSE
📎 4dac269c6054007bf10d3a08abdcab07.png
D7 | PREVENTION & REPLICATION TEMPLATE
I.RISK OF RECURRENCE ELSEWHERE
| Area / Line / Product | Similar Risk Present? |  | Action Taken
| Tianjin plant / AG-15 line / Part No. 382 | TRUE |  | Installed the automatic gluing device and implemented 100% visual check of copper wire to prevent glue contamination at the weld area.
FALSE
FALSE
II. LESSON LEARNING DISSEMINATION
| Audience / Team |  | Method (Meeting, LLC, Email) |  | Date | Owner |  |  | Evidence
| Production Grinding team; PQC |  | Shift briefing |  | 2026-05-29 | Alec YAO (Engineering Manager, Tianjin) |  |  | Shift briefing record / attendance sheet (to be filed)
III. Replication Validation
| Line / Site | Action Replicated |  |  | Confirmation Method | Confirmed By
| Tianjin / AG-15 | Automatic gluing device installation (replacing manual needle dispensing). |  |  | Visual check of 3000 pcs with acceptance criteria: 'no glue on copper wire'. | Bingren YUAN — Quality Supervisor (Quality Dept., Tianjin)
IV. Knowledge Base Update
| Document Type | Topic/Reference |  |  | Owner | Location / Link
| PFMEA | Add failure mode: glue overflow/contamination on copper wire/weld area leading to welding spark and shunt loosening; ensure it is flowed down to controls. |  |  | Alec YAO | AVOT-FMEA-JE-001-A2
| Control Plan | Add control item for glue overflow/contamination at weld area with defined control method and reaction plan. |  |  | Alec YAO | AVOT-CP-JE-009-A2
| WI | Update appearance selection inspection WI: copper wire surface not allowed to be contaminated with glue; any contamination = NG; include defect samples as reference. |  |  | Hongyan LI | AVOT-Q-20260529
V. Long-Term Monitoring
| Checkpoint Type |  | Frequency |  | Owner | Start Date |  |  |  |  | Notes
| Daily visual audit of copper wire glue contamination at weld area |  | Daily |  | Weijiang PENG | 2026-05-29 |  |  |  |  | Owner verified in directory: Weijiang PENG, Quality Manager, Tianjin.
VI. LL conclusion
📎 质量警报23-碳刷铜线污染CPUN54D0122.pdf
D8 | Closure & Capitalization
FINAL 8D CLOSURE STATEMENT (Is the customer sattisfied? Has the problem no -recurred? Has the team learned and improved? Are all actions documented, visible and stabilized?
Customer complaint for CPUN54D0122 carbon brush (spark emitted during welding and loosened shunt wire, 2 pcs found on 2026-05-27 at JE BU via visual inspection) has been addressed. Customer was notified and accepted the corrective action plan on 2026-05-29. Corrective actions are implemented and embedded in the system: automatic gluing device installed to eliminate manual needle dispensing and prevent glue overflow onto copper wire/weld area; Control Plan updated to include glue contamination failure mode with defined control and reaction plan; appearance inspection WI updated with clear criteria and reference samples. Effectiveness was verified with no recurrence observed (0 defects for 2 days across 2 lots after implementation). Relevant operators/PQC were trained on the updated WI/new gluing method and reaction plan on 2026-05-29, and the process is now controlled to prevent recurrence. Closed by: Weijiang PENG — Quality Manager, Quality Dept., Tianjin ¦ Date: 2026-06-05 ¦ Approved by: Weijiang PENG — Quality Manager, Quality Dept., Tianjin