## Sheet1
PROBLEM SOLVING - 8D METHOD ¦ 8D-20260312-163832 ¦ Brush holder with burr on inner cavity
D1 | Establishing a team
| Names and functions of the team members involved (Whether they have the authority and knowledge to contribute to solving the problem) | [8 empty] | Their roles in the process (e.g. Production, Quality, Maintenance, Engineering)
| Armando HERRERA — product line leader / production Matilde SERRANO — production manager / production | [7 empty] | TRUE | Production (operator, line leader, or supervisor)
| Alicio FLORES — project_manager / maintenance | [7 empty] | TRUE | Maintenance (if equipment is involved)
| Hector OLIVARES — project_manager / engineering | [7 empty] | TRUE | Process or Manufacturing Engineering
[9 empty] | FALSE | Logistics / Supplier Quality (if relevant)
| Gabriel FERNANDEZ — project_manager / quality | [7 empty] | TRUE | Team leader or project manager (if apply)
[9 empty] | FALSE | Quality
[9 empty] | FALSE | Other (if apply)
D2 | Problem Description
| BRUSH CARD (ASSEMBLY) produced at MONTERREY for NIDEC (Matamoros Plant 5 (Trico)) presents a burr on the brush holder inner cavity. This defect prevents assembly of the brush holder into the motor housing, affecting FRONT WIPER motor assembly. Issue linked to PLASTIC INJECTION; classified as high priority (quality type: CS1). WHAT: Brush holder has a burr on the inner cavity. WHERE: NIDEC Matamoros Plant 5 (Trico) production line during installation into the motor housing. WHEN: Customer complaint: 2025-10-13 WHO: Customer production line operator WHY: The burr blocks fitment, so the brush holder cannot be assembled into the motor housing, impacting Front Wiper motor assembly. HOW: Detected during installation attempt of the brush holder into the housing on the production line. HOW MANY: 3 pieces Expected: Brush holder inner cavity is free of burrs and allows proper fit/assembly into the motor housing. Observed: Customer found a brush holder with a burr on the inner cavity, causing a fit/assembly issue (parts cannot be assembled on motor housing). |  |  |  |  | III. Photo of defected part or schema of deviated measurement
| II.Factor | Is a Problem |  | Is Not a problem
|  | Other part numbers/ customers/sites affected/lot affected |  | Part numberscustomers//sites not affected/lot numbers not affected
| Product | Brush holder PN 33-0155 from molding cavity 16 shows burr on inner cavity causing no-fit into motor housing |  | Brush holder PN 33-0155 from other molding cavities (not cavity 16) shows no burr and fits into motor housing
| Time | Manufactured on 2025-10-07, 2025-10-09, and 2025-10-10; complaint detected on 2025-10-13 during assembly at customer line |  | Other manufacturing dates outside 2025-10-07/09/10 (not reported to show the burr/no-fit condition)
| Lot | Lots 279, 281, 282 (linked to cavity 16) contain the reported defect parts |  | Lots other than 279, 281, 282 (or parts not from cavity 16) not reported to contain burr/no-fit
| Pattern | 3 NOK pieces with burr/no-fit (3/113,590 total pieces in the sorted population) |  | Sorting results show 0 additional defects found: 36,790 pcs at customer + 76,800 pcs at Assymex
D3 | Containment Actions |  |  |  |  | 📎 Capture d’écran_12-3-2026_165551_avocarbon.monday.com.jpeg
| I. Defected part status | TRUE | Is it returned to AVOCarbon? | TRUE | Isolated — AssyMex quarantine area (MRB/quarantine) | 📎 Capture d’écran_12-3-2026_165611_avocarbon.monday.com.jpeg | TRUE | Identified: Red tag applied (no serial number). Returned from customer and quarantined at AssyMex on 10/10/2025.
📎 Picture2 lot.png
📎 Picture3 lot.png
| Location | Inventory |  | Actions |  | 📎 Picture4 lot.png |  |  |  | Results
Supplier site
In Transit
In Production floor
| In Warehouse | 76800 pcs |  | Containment and 100% sorting of suspect inventory at AssyMex plant warehouse. |  | Alfredo Herrera |  |  |  | 76800 pcs sorted on 10/10/2025; 0 NOK found; all OK released.
| In customer site | 36790 pcs |  | Containment and 100% sorting of suspect inventory at customer line and warehouse (performed by Sortech). |  | Sortech |  |  |  | 36790 pcs sorted on 10/10/2025; 0 NOK found; all OK released.
Others
| III. Alert Comunicated to | TRUE | Production Shift Leaders | TRUE | Warehouse |  | FALSE | Customer Contact
| Alert # (QRQC log or NCR #): Issued - no number (pending) | TRUE | Quality Control | TRUE | Maintenance |  | FALSE | Production Planner
| IV. Restart Production |  | 2025-10-17 |  |  | 2025-10-17 |  |  |  | Green dot in the label box to identify certified parts
Gabriel FERNANDEZ – Quality Manager (Quality, Site-Mexico)
100% visual sorting for inner cavity burr: 100% sorted by supplier + 100% in-process sorted by operator
| V. Containment Responsible: | Gabriel FERNANDEZ – Quality Manager (Quality, Site-Mexico)
D4 | Root Cause Analysis
I. Define potential root cause for 4M+ Environment -OCCURRENCE
| Material |  | Method |  | Machine
| Resin lot/viscosity variation could increase flash tendency (not selected). |  | Mold PM standard/checklist did not include CTQ check for insert shut-off wear at inner-cavity parting line. |  | Injection mold insert shut-off wear at parting line created a gap, generating consistent flash on inner cavity.
| Not indicated. |  | No CTQ identification for shut-off wear, so inspection/acceptance criteria were not defined in the maintenance plan. |  | Localized wear at insert shut-off/parting line corresponds to consistent flash location.
| Not indicated. |  | Incoming condition: parts received with flash from supplier molding process. |  | Mold condition at supplier (Assymex) drives defect generation. |  |  |  | Injection mold insert shut-off wear at parting line created a gap, generating flash/burr on inner cavity.
| Manpower |  | Environment
| Maintenance/production team followed existing PM standard; no defined check for this wear point (not selected). |  | Not indicated. |  | T1
| Not indicated. |  | Not indicated. |  | T2
| Not indicated. |  | Not indicated. |  | T3
II. 5 Whys (Ocurrence) for selected Root causes
| 1st Why? | Question: | Why did the brush holder have a burr/flash on the inner cavity that blocked assembly?
|  | Answer: | Because molding flash was generated at the inner-cavity parting line (insert shut-off), creating an interference.
| 2st Why? | Question: | Why was flash generated at that parting line/insert shut-off?
|  | Answer: | Because the insert shut-off was worn, creating a gap that allowed material to flash.
| 3st Why? | Question: | Why did the insert shut-off become worn to the point of creating a gap without correction?
|  | Answer: | Because the preventive maintenance standard/checklist did not include a check for shut-off wear at that location.
| 4st Why? | Question: | Why was the shut-off wear check missing from the PM standard?
|  | Answer: | Because shut-off wear at the inner-cavity insert was never defined/identified as a CTQ in the mold maintenance plan.
| 5st Why? | Question: | Why was the CTQ not identified for that shut-off area?
|  | Answer: | Not confirmed (not provided).
| Injection mold insert shut-off wear at the inner-cavity parting line (supplier mold) created a gap, producing consistent molding flash/burr on received brush holders. |  |  | Before/after parts comparison after insert replacement (confirm flash eliminated post-replacement).
IV. Define potential root cause for 4M+ Environment-NON DETECTION
| Material |  | Method |  | Machine
| Manpower |  | Environment
T1
T2
T3
V. 5 Whys (Non Detection) for selected Root causes
| 1st Why? | Question:
Answer:
| 2st Why? | Question:
Answer:
| 3st Why? | Question:
Answer:
| 4st Why? | Question:
Answer:
| 5st Why? | Question:
Answer:
D5 | CORRECTIVE ACTION | [6 empty] | D6. I. Implementation & Effectiveness Check
| I.Corrective Action for Occurrence |  |  |  | Responsible | Due Date |  | Imp Date |  | Evidence
| Include insert review in Preventive Maintenance to detect any insert damage before production. |  |  |  | Ramses Rendon (Production, Product line leader) | 2025-10-15 |  | 2025-10-15 |  | MI-IM03-I02-V01
| Repair the mold insert to eliminate the gap against the mold to prevent burr generation (no parts with burr). |  |  |  | Orlando Salazar (Production, Product line leader) | 2025-11-29 |  | 2025-11-29 |  | MI-IM03-I01-V01
| II.Corrective Action for Detection |  |  |  | Responsible | Due Date |  | Imp Date |  | Evidence
D6 | II. Implementation & Effectiveness Check |  |  |  | III. Implementation & Effectiveness Check |  |  |  |  | Shift 1 | Shift 1 | Shift 1
| Monitoring intervale of time |  |  |  | Have parameters been corrected in safety/ working instructions? |  |  |  |  | FALSE | FALSE | FALSE
| Number of pieces produced |  |  |  | Do working instructions match with Control Plan and PFMEA? |  |  |  |  | FALSE | FALSE | FALSE
| Rejection rate |  |  |  | Are the instruction clear? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Are crtitical points clearly described? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Does actual process match with the operating instructions |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Does actual process match with the expected corrective actions? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Are operators aware of the incident? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Are operators training about all process modification? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Has the solution properly validated in the floorshop? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Is there a clear visual aid published in visible spot? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Is the equipment modified vs the corrective actions? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Is the maintenance record modified? |  |  |  |  | FALSE | FALSE | FALSE
[5 empty] | Is the set up instruction modified? Match with CP? |  |  |  |  | FALSE | FALSE | FALSE
D7 | PREVENTION & REPLICATION TEMPLATE
I.RISK OF RECURRENCE ELSEWHERE
| Area / Line / Product | Similar Risk Present? |  | Action Taken
| MONTERREY – ASSEMBLY – Brush holder (affected PN) | TRUE |  | Reviewed all brush-holder PNs and confirmed only this PN uses that supplier mold/insert (confirmed by Ramses RENDON). Added insert condition review into Preventive Maintenance to detect insert damage before production; implemented 2025-10-15.
FALSE
FALSE
II. LESSON LEARNING DISSEMINATION
| Audience / Team |  | Method (Meeting, LLC, Email) |  | Date | Owner |  |  | Evidence
III. Replication Validation
| Line / Site | Action Replicated |  |  | Confirmation Method | Confirmed By
| MONTERREY – ASSEMBLY | Insert condition review added to Preventive Maintenance plan |  |  | PM checklist updated and implemented on 2025-10-15; insert condition review performed prior to production | Ramses RENDON (Production, Product line leader)
IV. Knowledge Base Update
| Document Type | Topic/Reference |  |  | Owner | Location / Link
V. Long-Term Monitoring
| Checkpoint Type |  | Frequency |  | Owner | Start Date |  |  |  |  | Notes
VI. LL conclusion
D8 | Closure & Capitalization
FINAL 8D CLOSURE STATEMENT (Is the customer sattisfied? Has the problem no -recurred? Has the team learned and improved? Are all actions documented, visible and stabilized?
Se notificó al cliente el resultado del 8D y confirmó su satisfacción. La causa raíz de ocurrencia fue el desgaste del shut-off del inserto del molde de inyección en Assymex en la línea de partición de la cavidad interna, lo que generaba rebaba/flash e impedía el ensamble al housing. Tras la reparación/reemplazo del inserto y la validación con comparación antes/después, no se ha observado recurrencia hasta el 2025-12-02. Las acciones correctivas y preventivas quedaron registradas y controladas en el sistema 8D, incluyendo la revisión del inserto en el plan de Mantenimiento Preventivo. Se capacitó a los líderes de mantenimiento de Turno 1 y Turno 2 el 2025-12-02 para asegurar la correcta ejecución y sostenimiento. Closed by: Marco Aguilar — Quality Engineer ¦ Date: 2025-12-14 ¦ Approved by: Gabriel Fernandez — Quality Manager