## QCR
Assymex Monterrey S.A. de C.V.
QUALITY CONTROL REPORT (10D)
QCR | [7 empty] | Date: |  |  |  |  | 2025-02-20
AssyMex Contact / Title: |  | Astrid López | [5 empty] | Customer Contact / Title: |  |  |  |  | Małgorzata Wandzel
Contact Phone: |  | +528181272830 | [5 empty] | Contact Phone: |  |  |  |  | +48 33 470 88 57
Email: |  | astrid.lopez@avocarbon.com | [5 empty] | Contact Email: |  |  |  |  | mwandzel@tifs.com
ONLY FILL THIS SECTION FOR INTERNAL SITUATIONS DETECTED AT ASSYMEX PLANT
|  | INTERNAL PPM | [6 empty] | INTERNAL AUDIT BY IATF
|  | EXTERNAL AUDIT BY CUSTOMER | [6 empty] | INTERNAL METRIC:
|  | EXTERNAL AUDIT BY IATF | [6 empty] | OTHER:
ONLY FILL THIS SECTION FOR QUALITY PROBLEMS DETECTED WITH CUSTOMER
Level 1 - Customer Return - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 2 - Quality Rejection - Immediate containment actions are required for all In House and Incoming stock
within 24 hrs. Product Return Approval (RMA) may be necessary.
Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
Level 3 - Quality Concern - Description of Root Cause & Corrective Action Plan are mandatory within 5 days.
All Incoming stock 100% certified.
Level 4 - Notification - All Incoming stock 100% certified.
WHAT IS THE PROBLEM ? > Use 4W + 2H to know what is the Current Situation ? Customer View and AssyMex View
- What happened? Description of the Problem |  | Parts found with slot on wrong side of brush | [7 empty] | - Why is it a problem? |  | Incorrect operation of parts
BAD PART | [9 empty] | GOOD PART
- When it happened? Date: dd-mm-yyyy |  | 2025-02-20 | [6 empty] | - Where detected? Incoming, Production Line, Customer, Warranty, etc. |  |  | TI WAP
- How detected? |  | Visual | [6 empty] | - How many bad parts? |  |  | 3
Additional Information for Customer
Customer Part Number: |  | HA500055022401 | [7 empty] | AssyMex Part Number: |  |  | 05-0491M
Customer Lot Number: |  | DN 65114 TI lotto 2435400380 | [7 empty] | AssyMex Lot Number: |  |  | WLD7/25/043/T1 12/02/2025
[10 empty] | Additional Information: |  |  | WLD7/25/042/T1 11/02/2025
WLD7/24/333/T1 28/11/2024
WLD7/24/340/T1 05/12/2024
WLD7/25/041/T1 10/02/2025
WLD7/25/044/T1 13/02/2025
Customer Inventory: | [9 empty] | AssyMex Inventory: |  |  | 10,800 pcs
In Transit Inventory: |  | 0 pcs | [5 empty] | Logistic Platform Inventory: |  |  |  |  | 0 pcs
Material Disposition
|  | Return to Supplier. | [5 empty] | Sort by Supplier. | [5 empty] | Sort / Rework by External Company
|  | RMA # | [11 empty] | WO #
|  | Scrap. Supplier's expense. | [5 empty] | Use as received | [5 empty] | Sort / Rework by AssyMex
WO #
CORRECTIVE ACTION REPORT - 10D REPORT
1.- | Problem Solving Team Members
| Leader: | Astrid Rivera | [5 empty] | Title: | Quality Engineer |  |  |  |  | Phone: | +528181272830
| Email: | astrid.lopez@avocarbon.com | [5 empty] | Fax: | [5 empty] | Mobile:
| Group: | Marco Estrada,Daniel Morales, Ramses Rendon, Alicio Flores, Armando Herrera,Lucero Calderon
2.- | Describe the Problem
Customer found in their production line parts where the slot is on the wrong side of the brush.
| - Was part reworked by supplier ? |  |  | No | [5 empty] | - When was it manufactured ? |  |  |  | 2024/8/22 to 2024/10/19
| - Are we capturing the defect when reinjecting product in normal process ? If YES, explain how ? |  |  | No | [5 empty] | - Did a similar problem happen previously at AssyMex or internally ? If YES, when ? |  |  |  | No
3.- | Immediate Countermeasures / Problem Containment ? (24 hours)
IMMEDIATE COUNTERMEASURES IN SUPPLIER PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
IMMEDIATE COUNTERMEASURES IN AssyMex PERIMETER | [8 empty] | RESPONSIBLE |  |  | DATE |  |  | WHERE?
100% visual inspection of parts with reversed tamping defect | [8 empty] | Astrid López |  |  | 2025-02-20 |  |  | Assymex Plant
Sorting Activity >> by Supplier
|  |  | Total Sorted |  | Total Bad Parts |  | PPM |  |  | Sorting Date | Responsible |  | Identification of OK Parts
|  |  | 12228 |  |  | = | '----'
- Suspect Inventory in AssyMex plant : |  |  | 10800 |  | 0 | = | '----' |  |  | 2025-02-21 | Astrid Lopez
- Suspect Inventory in Transit : |  |  | 0 |  |  | = | '----'
- Suspect Inventory in Logistic platform : |  |  | 0 |  |  | = | '----'
- Suspect Inventory in Supplier plant : |  |  | 0 |  |  | = | '----'
- Production dates of sorted parts: |  |  | From: |  |  | To: | [5 empty] | First Certified Good Shipment |  |  | Lot Number:
|  |  | 2024-11-28 |  |  | 2025-02-13 | [8 empty] | WLD7/25/051/T1
- Production dates of bad parts: |  |  | Oldest part: |  |  | Most recent part: | [8 empty] | Date:
2025-02-20
4,1.- | Analysis and Root Cause - Ocurrence
5 x Why Analysis Form - Ocurrences Why did it happen?
1st Why? | Question: | Why were assemblies prduced with wrong finish on the face of the brush?
| Answer: | Because the slot of the brush is on the wrong side
2nd Why? | Question: | Why the slote of the brush is on the wrong side?
| Answer: | Because the block is tamped in backwards
3rd Why? | Question: | Why the block is tamped in backwards?
| Answer: | Beacuse the block was placed in the guide backwards
4th Why? | Question: | Why the block was placed in the guide backwards?
| Answer: | The guide feeder allows the block to be placed backwards
5th Why? | Question:
Answer:
4,2 .- | Analysis and Root Cause - Non Detection
5 x Why Analysis Form - Non-Detection Why did the non-conformity escape?
1st Why? | Question: | Why was brush with slot on the face not detected?
| Answer: | Because criterio was not established in inspection instruction
2nd Why? | Question: | Why wa criterio not established in inspection instruction?
| Answer: | Beacuse criterio was not established in control plan
3rd Why? | Question:
Answer:
4th Why? | Question:
Answer:
5th Why? | Question:
Answer:
5.- | Corrective Action
To Eliminate Occurrence of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Place a sensor that detects the correct position of the block in the guide (stop machine when detecting a block backwards) |  |  |  |  | Eliminate the occurrence of placing the block backwards on the machine guide | [6 empty] | Alicio F. | 2025-03-25 | Ongoing
| Update work instruction with the correct feeding method on the machine |  |  |  |  | Eliminate the occurrence of placing the block backwards on the machine guide | [6 empty] | Astrid L. | 2025-03-26 | Ongoing
| Update work instruction with the reaction plan when the sensor stops the machine for a reverse block |  |  |  |  | Eliminate the occurrence of placing the block backwards on the machine guide | [6 empty] | Astrid L. | 2025-03-26 | Ongoing
| Update set-up sheet with the function of the sensor |  |  |  |  | Eliminate the occurrence of placing the block backwards on the machine guide | [6 empty] | Ramses R. | 2025-03-26 | Ongoing
To Improve Detection of the Problem:
| Corrective Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Update work instruction with correct criterio for reversed tamping on brush |  |  |  |  | Detect the defect on real time and correct the problem | [6 empty] | Astrid L. | 2025-03-21 | Ongoing
| Update control plan with correct criterio |  |  |  |  | Correctly document the defect in the production line | [6 empty] | Astrid l. | 2025-03-28 | Ongoing
| Update AMEF with correct criterio |  |  |  |  | Correctly document the defect in the production line | [6 empty] | Astrid l. | 2025-03-28 | Ongoing
6,1.- | Implement and Verify Corrective Action - Occurences
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influent Factors
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
3- IS ALL DOCUMENTATION COHERENT?
4- ARE THE INSTRUCTIONS CLEAR?
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
8- ARE OPERATORS AWARE OF THE DEFECT?
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid
11- IS THERE A VISUAL AID?
12- IS IT POSTED ON A VISIBLE SPOT?
13- IS THE CONTENT CLEAR?
Equipment
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
6,1.- | Implement and Verify Corrective Action - Non - Detection
Checks | CONFIRMATION CHECKS | [8 empty] | CHECK QUALITY PER SHIFT
[10 empty] | 1st |  | 2nd |  |  | 3rd
Confirmation of Influential Factors
1- HAVE PARAMETERS BEEN CORRECTED IN SAFETY / WORKING INSTRUCTIONS?
2- DO WORKING INSTRUCTIONS MATCH WITH QUALITY CONTROL PLAN?
3- IS ALL DOCUMENTATION COHERENT?
4- ARE THE INSTRUCTIONS CLEAR?
5- ARE CRITICAL POINTS CLEARLY DESCRIBED?
Physical Check of Operation
6- DOES ACTUAL PROCESS MATCH WITH THE OPERATING INSTRUCTIONS?
7- DOES ACTUAL PROCESS MATCH WITH EXPECTED CORRECTIVE ACTION?
8- ARE OPERATORS AWARE OF THE DEFECT?
9- ARE OPERATORS AWARE OF THE EXPECTED CORRECTIVE ACTION?
10- HAS THE SOLUTION BEEN PROPERLY VALIDATED ON THE FLOOR?
Visual Aid
11- IS THERE A VISUAL AID?
12- IS IT POSTED ON A VISIBLE SPOT?
13- IS THE CONTENT CLEAR?
Equipment
14- IS IT COHERENT WITH THE CONTENT OF THE CORRECTIVE ACTION?
15- HAS IT BEEN MODIFIED? IS PREVENTIVE MAINTENANCE RECORD MODIFIED?
16- IS SET UP INSTRUCTION UPDATED? MATCHES WITH CONTROL PLAN?
Quality Control Documentation
17- WAS THE PLAN CONTROL WITH THE CORRECTIVE ACTIONS UPDATED?
18.- WAS THE PROCESS FMEA UPDATED WITH THE CORRECTIVE ACTIONS?
19.- WAS THE WORK INSTRUCTION UPDATED WITH THE CORRECTIVE ACTIONS?
20.- WAS THE QUALITY REGISTER UPDATED WITH THE CORRECTIVE ACTIONS?
AUDITOR'S NAME | [6 empty] | DATE OF THE AUDITS
Comments | [6 empty] | DECISION |  |  | Y |  | Y |  |  | Y
[10 empty] | N |  | N |  |  | N
7.- | Preventive Action
| Preventive Action |  |  |  |  | Expected result efficiency | [6 empty] | Who | Due Date | Done Date
| Update preventive maintenance for the correct function of the sensor |  |  |  |  | Prevent sensor malfunction in the machine | [6 empty] | Ramses R. | 2025-03-28 | Ongoing
| Update control plan with correct criterio and parameters of new sensor |  |  |  |  | Follow-up of actions to correct the problem | [6 empty] | Astrid l. | 2025-03-28 | Ongoing
| Update AMEF with correct criterio and parameters of new sensor |  |  |  |  | Follow-up of actions to correct the problem | [6 empty] | Astrid l. | 2025-03-28 | Ongoing
8.- | Standardize / Potential Applicability
| 1.- Potential Applicability of Corrective / Preventive Action to similar lines / products. | [12 empty] | Comments
| To whom? | Production Line: | [6 empty] | When?
|  | Operation: | [6 empty] | When?
|  | Product: | [6 empty] | When?
9.1.- | Evidence your Efforts - Ocurrences
Before Corrective Action | [9 empty] | After Corrective Action
9.2.- | Evidence your Efforts - Non Detection
Before Corrective Action | [9 empty] | After Corrective Action
10.- | Congratulate the Team
Man power
Method
Enviromental
Machine
Material
Measurements
Reversed Tamping
-Brush with double slot
-Feeder allows to place the block backwards
-Method of block feeding on tamping machine unclear
Man power
Method
Enviromental
Machine
Material
Measurements
Non-Detection Reversed Tamping
-Insufficient light
-Poor inspection
-No magnifying glass was used for inspection
-Mixing of brushes (defective brushes)
-Inspection instruction does not mention the defect
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
Process Before CA
Picture / Description of Process Before Corrective Action
Process After CA
Picture / Description of Process After Corrective Action.
-Slot on opposite side of cable
-Slot on cable side
-Smooth brush face with serration lines
Note on F145: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Sorting has not started yet
Note on K145: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: Sorting has not started yet
Note on F146: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: We still sorting the material in today sorting we didn´t find any material with the defect, we´ll update the report when we finish the sorting
Note on K146: [Comentario encadenado] Su versión de Excel le permite leer este comentario encadenado; sin embargo, las ediciones que se apliquen se quitarán si el archivo se abre en una versión más reciente de Excel. Más información: https://go.microsoft.com/fwlink/?linkid=870924 Comentario: We´ll finish the sorting on this date
Note on B156: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B233: Root-cause From the conclusions of the analysis (Factor Tree Analysis, Reproduction of the defect, 5 whys), report the root-cause of the problem needing a correction.
Note on B312: Corrective action Explain clearly which corrective actions are implemented to correct the root-cause. Reader should understand what is the difference between previous and future situation. Put data when appropriate, process parameter before and after for example. Define Due Dates for each Corrective Action.
Note on B338: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K340: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H374: Date of the audit: For every shift, record the date of audit
Note on H376: Decision: Tick Y or N to validate or not the result of the audit for each shift.
Note on B382: Confirmation checks - According to the corrective actions decided to solve the issue, the correct implementation of each action must be checked by the quality engineer with fact and data. - The check is done on each shift including.
Note on K384: Check by quality per shift - Put OK/NOK to formalize the audit result
Note on H426: Date of the audit: For every shift, record the date of audit
Note on H428: Decision: Tick Y or N to validate or not the result of the audit for each shift.

## Add - Visual Aid
WHEN I FIND A BAD PART, WHAT SHOULD I DO?
Adhere to Quality Alert visual
Follow Reaction Plan: Stop operation after finding a defective part, call maintanence and the supervisor
PROHIBITED OPERATIONS:
Non-inspection
PERMITTED TOOLS:
Quality Alert
Pull test to validate process
LEVEL | A | B | C | D | E | F | G
DATE LEVEL | 2025-02-20
WHO CREATE | A.L
Visual Aid
Describe the defect
Bad part
Good part
Detached solder from pin to brush wire
Pin with correctly soldered brush without detachment

## LLC Occ
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## LLC NON-DET
| LESSON LEARNED CARD |  |  |  | Type | Share the LLC? | Department
[5 empty] | Occurrence | Yes | Quality
[5 empty] | Detection | No | Production
Site: |  | Type: |  | CIN: | Management | N/A | Logistics
Production Line: |  | Department: |  | SIN: | Logistics |  | Maintenance
Product: |  | LLC Author: |  | Date: | Internal |  | Engineering
WHAT WAS THE PROBLEM? (5W + 2H) |  | WHAT IS THE SYMPTOM? |  |  | Supplier
What happened?
Why is it a problem?
When did it happen?
Who detected it?
Where was detected?
How was detected?
How many?
BEFORE |  |  | AFTER
WHAT WE LEARNED?
ITEM (Control Factor) | METHOD (Control Point) |  |  | STANDARD
| What? |  |  | What is Conform?
Where?
When?
| Who? |  |  | What is Non-Conform?
How?
How Many?
Note on E5: Choose from the list the type of LLC
Note on H5: Customer Incident Number leave cell in blank for Internal Type of LLC
Note on E6: Choose from the list the department responsible for the current LLC
Note on H6: Supplier Incident Number leave cell in blank for Internal Type of LLC
Note on H7: Date of LLC creation
Note on E9: Add a picture and description which explains the problem. (BAD PART)
Note on H9: Add a picture and description which explains how a good part should be. (OK PART) Picture must be the same size and angle than Bad Part picture
Note on B24: - Occurence. Add a picture and description which explains the conditions that led to the problem. - Detection. Add a picture or a descriptive graph which explain the process of validation/control. - Management.
Note on F24: Add a picture and description which explains the countermeasure on the part/process.
Note on D44: Explain what, how, when, who to perform correct measurement of the Item (Control Factor). Also define how many parts have to be measured.
Note on B45: Describe, what you have learnt and what needs to be put under control.
Note on H46: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.
Note on H52: To be able to judge the result of the factor measurement, specify: What is in conformance? Add a picture and/or an explanation.

## Evidence Control Plan and PFMEA
CONTROL PLAN
PFMEA
INSERT HERE SCREENSHOT
OF CONTROL PLAN UPDATED
INSERT HERE SCREENSHOT
OF PFMEA UPDATED