## 8D
| TRICO | 8D WORKSHEET | [6 empty] | CAR #
[9 empty] | CUSTOMER CONCERN # | 18968
CUSTOMER NAME |  | Trico Matamoros |  |  |  |  | TRICO PART # |  | 95015-101
CUSTOMER PLT. LOCATION | [6 empty] | CUSTOMER PART # |  | NA
TRICO PLT. AFFECTED |  | Matamoros |  |  |  |  | ASSY. DESCRIPTION |  | Brush plate
TRICO DEPT. NAME |  | Motors |  |  |  |  | COMPONENT PART # |  | NA
ROOT CAUSE CODE |  | Noise |  |  |  |  | COMPONENT DESC. |  | NA
REPEAT ISSUES |  | No |  |  |  |  | QCR # |  | 18968
PROBLEM DESCRIPTION |  | Burr in retainer |  |  |  |  | SEVERITY (1-3) |  | 1
Revision History: Indicate original Response Due Date and date of any extension requests.
| Date | Description Revision | [6 empty] | 8D Due Date |  | Supplier 8D Due Date
| 2025-07-24 | Create QCR
[9 empty] | Open / Closed |  | Level
Due Date Extension Request
[9 empty] | Requested On |  | Extension To
D1 - Team Members:
| Miguel J. |  | Quality Engineer |  |  | Alicio Flores |  |  | Engineering Manager
| Ramses Rendon |  | Maintenance coordinator |  |  | Héctor Olivares |  |  | Deputy Plant Manager
| Orlando Salazar |  | Production Coordinator
| Daniel Morales |  | Quality Manager
D2 - Concern Description:
| Customer reported the following issue: |  | TRICO VIEW: ASSYMEX VIEW: Burr in the brush retainer mold's ejector pins area
| Concern was received via: |  | E-Mail |  |  |  |  | Date Customer reported Concern: |  |  | 2025-07-24
| Customer's Department / Area which found issue: |  | Quality
| Person at Assembly Plant reporting issue (Name & Title): |  |  |  | Martin Sosa / SQE
| Phone #: |  |  | Fax #: |  |  |  | Email: | Martin.sosa@tricoproducts.com
| Number of pieces reported by the Customer |  |  | Platform |  | Date Plt 4 Rec. Samples |  |  | Date Plt 5 Rec. Samples
15
D3 - Containment Action & Verification:
| Is containment on assemblies necessary? - Explain why or why not. |  | Yes. It is necessary, our customer must to receive certified product.
| Who at Trico will be doing the containment on assemblies? Indicate Name(s) & Dept(s). |  | Hold area
| Define containment activity. |  | Retainer brush (16-0066M) segregation with plastic burr
| Where at Trico will containment take place? - Indicate Plant(s) & Dept(s). |  | Plant 5 / hold area
| Will the Containment activity chosen have an impact on the customer? - Explain why or why not. |  |  |  | our containment activity won´t affect customer shipment
FINISHED GOODS CONTAINMENT
| Location | Quantity Available | Sort Results |  |  |  | Disposition
|  |  | Quantity Accepted |  | Quantity Rejected
| Trico plant | 100,000 pcs | TBD |  | TBD
| Assymex Plant | Finish good: 50,000 pcs inventory: 5,000 pcs Plastic line: 20,000 pcs | TBD |  | TBD
D4 - Root Cause and Verification:
| Cause & Effect Diagram Generated? | (Yes,No,N/R) |  |  |  | Root Cause is: |  |  | (Common, Special)
| Turned Problem On & Off? | (Yes, No) |  |  |  | Physical Root Cause Identified? |  |  | (Yes, No)
| Proprietary Information Involved? | (Yes, No) | [6 empty] | Please explain in root cause.
[6 empty] | Systemic Root Cause Identified? |  |  | (Yes, No)
Please explain in root cause.
Root Cause Discussion: Plastic burr in the brush retainer mold's pin area
Why: The plastic leaked from the area where the mold's ejector pin ejectors are located. Why: The ejector pins did not seal correctly and completely during the injection cycle. Why: The ejector pins do not make contact with the mold surface Why: The ejector pins in the cavity broke Why: Wear and tear due to use and stress. Why: Specific root cause: the ejector pins were used in the process beyond their useful life.
Why: There is no system for detecting or monitoring the condition of the inyector pins Why: It is assumed that the injector pins are in good condition while the mold is in operation since there are no burrs in that area of the part. Why: There is no specific inspection control to verify wear or damage to the ejector pins between production runs, at the end of a run, or at the start of the next. Why: Because the only check established for the ejector pins system is during preventive maintenance, which is periodic maintenance and is not performed between each run. Why: Detection root cause: There is no method for inspecting or functionally verifying the condition of the mold's ejector pins before and after each production run.
D5 - Corrective Action (s) & Verification
| Pareto Analysis performed? | (Yes, No, N/R) |  |  |  | ECR Required? |  |  | (Yes, No)
| Mistake Proofing Implemented? | (Yes, No) |  |  |  | PPAP Required? |  |  | (Yes, No)
| Corrective Action Discussion: |  |  |  |  | Person Responsible |  | ECD |  | ACD
| Creation and deployment of the quality alert. |  |  |  |  | Miguel Jasso |  | 2025-07-24 |  | 2025-07-24
| Inform stakeholders about the quality issue and train them about the quality alert. |  |  |  |  | Miguel Jasso |  | 2025-07-24 |  | 2025-07-24
| Containment of material in inventory, plastics line, material in assembly process and finished product |  |  |  |  | Miguel Jasso
| Conduct containment training and train the personnel who will perform the activity |  |  |  |  | Miguel Jasso |  | 2025-07-24 |  | 2025-07-24
| Conduct material sorting according to the material containment instructions and place a certification label with the legend "Material without burrs in the area of the ejector pins." |  |  |  |  | Miguel Jasso
| Replacing damaged mold ejector pines |  |  |  |  | Orlando Salazar. |  | 2025-07-25 |  | 2025-07-25
D6 - Implementation of Permanent Corrective Action (s) & Verification
| Permanent Corrective Action & Verification: |  |  |  |  | Person Responsible |  | ECD |  | ACD
| Manufacture gage for detection of burrs and excess plastic in the brush retainer plunger area, 16-0066M |  |  |  |  | Alicio Flores |  | 2025-07-25 |  | 2025-08-01
| Update the first-piece inspection format and release sheet hourly, including checking the parts with a gage to detect burrs in the ejector pin area. |  |  |  |  | Miguel Jasso |  | 2025-07-25 |  | 2025-08-01
| Date complete. | 2025-01-08
D7 - Prevent Recurrence
| Prevent Recurrence: |  |  |  |  | Person Responsible |  | ECD |  | ACD
| Update FMEA, Control Plan, and self-monitoring sheet, including the defect, risks, and controls to mitigate the problem. |  |  |  |  | Miguel Jasso |  | 2025-07-28 |  | 2025-08-04
| Prepare a mold preparation checklist that includes checking the ejector pins for completeness, wear, and lubrication before and after each production run. |  |  |  |  | Ramses Rendón |  | 2025-07-28 |  | 2025-08-08
D8 - Congratulate the Team - Recognize the collective efforts of the team.
Trico 8D Closure Date
Customer Contact and General Log Section
| Step | Date | Details
Customer 8D Closure Date
Note on B23: Input the Team Members' names, activities, and phone numbers (include ext.).
Note on B28: Specify the internal / external customer problem by identifying in quantifiable terms What, When, Where, Why (is it a problem) and How Many.
Note on B43: Define containment activity by identifying in quantifiable terms the Who (Plant 1, 2, Customer, etc.), What, When (start and end dates), Where, Why and How Many of the action.
Note on B59: Identify all potential causes using a Cause & Effect Diagram or similar tool. Isolate and verify the root cause by testing each potential cause against the problem description and provide test data. Determine if the root cause is common or special and systemic or physical. Verify, when practical, that the nonconformity can be turned On and Off. Indicate if information is proprietary and cannot be included in the 8D. Discuss in detail below.
Note on B71: Though pre-production tests confirm short-term corrective actions are effective, indicate if Pareto Analysis was performed & mistake proofing / Poka-Yoke were considered. Submit PCR, if required. Indicate if a PPAP is required. For all planned Corrective Action activities indicate the Estimated Completion Date (ECD) and Actual Completion Date (ACD).
Note on B85: Define and implement the best permanent corrective actions based on validation testing. Update all related documentation. Verify effectiveness of permanent corrective action through review of company level data and with customer. Once in production, monitor the long-term effects and implement contingency actions, if necessary. For all planned verification activities indicate the Estimated Completion Date (ECD) and Actual Completion Date (ACD).
Note on B94: Discuss any modifications to the management systems, operating / quality systems, practices, and procedures made to prevent recurrence of this and all similar problems/product. For all planned activities designed to prevent recurrence, indicate the Estimated Completion Date (ECD) and Actual Completion Date (ACD).

## Hoja1
CORRECTIVE ACTIONS EVIDENCE
Creation and deployment of the quality alert.
Manufacture gage for detection of burrs and excess plastic in the brush retainer plunger area, 16-0066M